## Gantt Chart
Mars Rover 2022
Group 7 |  | Project Start: | 2022-05-23
Jubo Xu/ Justin Huang/ Charlie Chen/ Jacky Jiang/ David Zheng/ Ziduan Li/ Rui Li |  | Today: | 2022-06-24
|  | Display Week: | 1 |  |  | 2022-05-23 | [6 empty] | 2022-05-30 | [6 empty] | 2022-06-06 | [6 empty] | 2022-06-13 | [6 empty] | 2022-06-20 | [6 empty] | 2022-06-27 | [6 empty] | 2022-07-04 | [6 empty] | 2022-07-11
 | time axis 2022-05-23 to 2022-07-17
TASK | ASSIGNED TO | PROGRESS | START | END | DAYS | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S
Energy
1. Characterise the P-V and I-V curve of PV panels | Rui Li | 100% | 2022-05-23 | 2022-05-25 | 3
2. Characterise the I-V curve of the power bank | Rui Li | 100% | 2022-05-23 | 2022-05-24 | 2
3. Come up with a general idea of the system | Rui Li | 100% | 2022-05-24 | 2022-05-26 | 3
4. Design of MPPT algoritm and testing | Rui Li | 100% | 2022-05-26 | 2022-06-03 | 9
5. Design of battery charing profile and testing | Rui Li | 100% | 2022-06-03 | 2022-06-12 | 10
6. Connect MPPT and battery charging profile | Rui Li | 100% | 2022-06-13 | 2022-06-20 | 8
7. Data collection and further improvement | Rui Li | 50% | 2022-06-20 | 2022-06-28 | 9
Drive
1. Assemble the rover &Optical Sensor Calibration | Justin Huang | 100% | 2022-05-23 | 2022-05-29 | 7
2. Implement Straight Line Control & Testing | Justin Huang | 100% | 2022-05-26 | 2022-06-02 | 8
2.1 PID Control Code Writing | Justin Huang | 100% | 2022-05-26 | 2022-05-29 | 4
2.2 PID Control Tunning and Testing with Position Control | Justin Huang | 100% | 2022-05-29 | 2022-06-02 | 5
3. Implement Position Control & Testing & Calibration | Justin Huang | 100% | 2022-06-02 | 2022-06-06 | 5
4. Implement Angle Control & Testing & Calibration | Justin Huang | 100% | 2022-06-06 | 2022-06-09 | 4
5. Command & Manual Control Testing | Justin Huang | 100% | 2022-06-09 | 2022-06-13 | 5
6. Integration & Control Testing | Justin Huang | 70% | 2022-06-13 | 2022-06-28 | 16
Command
1. (Front & Back-end) Function Definition & Design Outline | Jacky & David | 100% | 2022-05-23 | 2022-05-24 | 2
2. (Front & Back-end) Log-in / Authentication Page by Firebase | David | 100% | 2022-05-24 | 2022-05-27 | 4
3. (Front-end) Main dashboard webpage design (ReactJS & MUI) | Jacky | 100% | 2022-05-24 | 2022-06-13 | 21
3.1 Coordinates dashboard with Real-time Coordinates Data | David | 100% | 2022-05-24 | 2022-05-29 | 6
3.2 Map with Real-time Rover & Alien & Infrastructure Icon | Jacky | 100% | 2022-05-29 | 2022-06-12 | 15
3.3 Resources Navigation & Real-time Rover Status | Jacky & David | 100% | 2022-06-12 | 2022-06-13 | 2
4. (Back-end) Connect main dashboard and local database (Post & Get - NodeJS) | David | 100% | 2022-05-28 | 2022-06-07 | 11
5. (Control) Connect ESP-32 & database with Firebase real time database | David | 100% | 2022-06-08 | 2022-06-13 | 6
6. (Front & Back-end) Migrate to Firebase database | Jacky | 100% | 2022-06-14 | 2022-06-16 | 3
7. (Front-end) Mannual control panel | Jacky | 100% | 2022-06-14 | 2022-06-16 | 3
8. Integrate & Testing with Drive | Jacky & David | 100% | 2022-06-16 | 2022-06-19 | 4
Radar
1. Learn about doppler effect and the check the property of HB100 | Ziduan Li | 100% | 2022-05-23 | 2022-05-29 | 7
2. Collect and analyse the data of original IF signal | Ziduan Li | 100% | 2022-05-30 | 2022-06-02 | 4
3. Design and test the amplifier circuit | Ziduan Li | 100% | 2022-06-03 | 2022-06-05 | 3
4. Design and test the band-pass filter | Ziduan Li | 100% | 2022-06-06 | 2022-06-10 | 5
5. Design and test the peak detector | Ziduan Li | 100% | 2022-06-11 | 2022-06-13 | 3
6. Connect the circuit with ESP32 and locate the target | Ziduan Li | 100% | 2022-06-14 | 2022-06-16 | 3
7. Improve the accuracy of target location | Ziduan Li | 60% | 2022-06-17 | 2022-06-28 | 12
Control
1. Connect ESP-32 with WIFI | Jacky Jiang | 100% | 2022-06-02 | 2022-06-04 | 2
2. Connect ESP-32 with Firebase Realtime Database | Jacky Jiang | 100% | 2022-06-08 | 2022-06-10 | 3
3. Rover manual control testing | Charlie Chen | 100% | 2022-06-11 | 2022-06-12 | 2
4. Establish connection between ESP-32 with FPGA | Bob Xu | 100% | 2022-06-13 | 2022-06-14 | 2
5. Establish connection between ESP-32 with radar | Ziduan Li | 100% | 2022-06-15 | 2022-06-16 | 3
6. Route Planning | Charlie Chen | 100% | 2022-06-17 | 2022-06-18 | 3
7. Avoidance | Justin Huang | 50% | 2022-06-19 | 2022-06-28 | 10
Vision
1. Build the starter project | Charlie Chen | 100% | 2022-05-23 | 2022-05-24 | 2
2. Reasearch and finish the RGB to HSV Convertor | Charlie Chen | 100% | 2022-05-24 | 2022-05-26 | 3
3. Color Detection and Pixel Processing | Charlie Chen | 100% | 2022-05-26 | 2022-06-22 | 28
3.1 Finding the HSV Region for six Colours | Charlie Chen | 100% | 2022-05-26 | 2022-06-17 | 23
3.2 3x3 Kernel Filter | Jubo Xu | 100% | 2022-06-03 | 2022-06-12 | 10
3.3 Cutting the Upper Sreen | Charlie Chen | 100% | 2022-06-20 | 2022-06-22 | 3
4. Draw the bounding boxes | Charlie Chen | 100% | 2022-06-16 | 2022-06-19 | 4
5. Distance and Pixel Width Measurement | Charlie Chen | 100% | 2022-06-19 | 2022-06-21 | 3
6. Building Detection | Jubo Xu | 100% | 2022-06-12 | 2022-06-22 | 11
6.1 Contrast improvement | Jubo Xu | 100% | 2022-06-12 | 2022-06-17 | 6
6.2 Black and White pixel extraction | Jubo Xu | 100% | 2022-06-17 | 2022-06-20 | 4
6.3 Edge detection and bounding box generation | Jubo Xu | 100% | 2022-06-20 | 2022-06-22 | 3
7. UART Bits Design and Processing | Charlie Chen | 100% | 2022-06-21 | 2022-06-21 | 1
8. Integrate & Testing with Control | Charlie Chen | 100% | 2022-06-22 | 2022-06-22 | 1
Note on G6: DAYS: This column calculates the duration of the task in calendar days. The duration includes both the Start and End dates.